## Sheet1
User Stories | Start Points | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Goal | Sprint Tasks
As a Student, I would like to login to the application manually | 13 | 10 | 0 | 0 | 0 | 0 | Sprint 1 | Team Member
As a lecturer, I would like all the courses stored with codes and value names. | 5 | 0 | 0 | 0 | 0 | 0 | As a lecturer, I would like all the courses stored with codes and value names. | Neil Asplin
As a lecturer, I would like to be able to make changes to paper details. | 30 | 0 | 0 | 0 | 0 | 0 | As a lecturer, I would like all the courses stored with codes and value names. | Matt Paul
As a Student, I would like to enter the courses that I have passed and save my academic history. | 8 | 0 | 0 | 0 | 0 | 0 | As a Student, I would like to login to the application manually | Stalin Fernandes
As a Student, I would like to see available future papers, filtered by topic area, based on papers I have already completed. | 8 | 0 | 0 | 0 | 0 | 0 | As a Student, I would like to login to the application manually | Dale Lochrie
As a Student, I would like to be able to select a plan of study for up to four semesters. | 5 | 0 | 0 | 0 | 0 | 0
As a student, I would like to be able to save a plan of study in a format that can be emailed or printed. | 8 | 0 | 0 | 0 | 0 | 0
As a Student, I would like the application to manage my details. | 8 | 0 | 0 | 0 | 0 | 0
As a student, I would like to categorise the courses into topic areas. | 5 | 0 | 0 | 0 | 0 | 0
As a Student, I would like to automatically log in, so that I don’t have to log in multiple times. | 13 | 0 | 0 | 0 | 0 | 0
| Start Points | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Goal
Total Points Remaining | 103 | 10 | 0 | 0 | 0 | 0
[7 empty] | Sprint 2 | Team Member
[7 empty] | Task X | TM1
[7 empty] | Task Y | TM2
[7 empty] | Task Z | TM3
[7 empty] | Task B | TM4
[7 empty] | Sprint 3 | Team Member
[7 empty] | Task X | TM1
[7 empty] | Task Y | TM2
[7 empty] | Task Z | TM3
[7 empty] | Task B | TM4
[7 empty] | Sprint 4 | Team Member
[7 empty] | Task X | TM1
[7 empty] | Task Y | TM2
[7 empty] | Task Z | TM3
[7 empty] | Task B | TM4
Sprint Planning Meeting
Date and Time: 11/08/2016 @ 9:00AM
Team Capacity: 4 Spaces
Approach: Scrum Method
Total Time Allocation: 24 Hours (Allowing for 12 Hour Sprints)
Using GitHub: We will all join a GitHub Team for our group.
Rules
- Only PO, SM and TMs are allowed to talk in these meetings -
- 1) What we did last time 2) What we will do today 3) What stands in our way -